## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | Software Development | 136 days? | 26 October 2016 08:00 | 30 April 2017 17:00 |  | 0
1 | Yes | Auto Scheduled | Research | 1.5 days | 26 October 2016 08:00 | 27 October 2016 12:00 |  | 1
2 | Yes | Auto Scheduled | Find Appropirate Literature Relating To Human Perception | 4 hrs | 26 October 2016 08:00 | 26 October 2016 12:00 |  | 2
3 | Yes | Auto Scheduled | Identify and Note Sections Which Aid the Project Aim | 1 day | 26 October 2016 13:00 | 27 October 2016 12:00 | 2 | 2
4 | Yes | Auto Scheduled | Research Complete | 0 days | 27 October 2016 12:00 | 27 October 2016 12:00 | 3 | 2
5 | Yes | Auto Scheduled | Start Dissertaion Literary Review | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 1
6 | Yes | Auto Scheduled | Scenario Design | 11 days? | 27 October 2016 13:00 | 11 November 2016 12:00 |  | 1
7 | Yes | Auto Scheduled | Analyse Research to Determine Viable Scenarios For Experiment | 5 days | 27 October 2016 13:00 | 03 November 2016 12:00 | 4 | 2
8 | Yes | Auto Scheduled | Determine 2 Scenarios To present for the Experiment | 3 days | 03 November 2016 13:00 | 08 November 2016 12:00 | 7 | 2
9 | Yes | Auto Scheduled | Design Storyboards For Both Scenarios | 1 day? | 08 November 2016 13:00 | 09 November 2016 12:00 | 8 | 2
10 | Yes | Auto Scheduled | Gather Resources/Appertus Required To Implement Scenarios. | 2 days | 09 November 2016 13:00 | 11 November 2016 12:00 | 9 | 2
11 | Yes | Auto Scheduled | Scenario Design Complete | 0 days | 11 November 2016 12:00 | 11 November 2016 12:00 | 10 | 2
12 | Yes | Auto Scheduled | Experiment Design | 11 days | 11 November 2016 13:00 | 28 November 2016 12:00 |  | 1
13 | Yes | Auto Scheduled | Develop Storyboard For Data Collection For Scenario 1 | 2 days | 11 November 2016 13:00 | 15 November 2016 12:00 | 11 | 2
14 | Yes | Auto Scheduled | Develop Storyboard For Data Collection For Scenario 2 | 5 days | 15 November 2016 13:00 | 22 November 2016 12:00 | 13 | 2
15 | Yes | Auto Scheduled | From Both Storyboards Define Experiment Instructions (In Detal) | 4 days | 22 November 2016 13:00 | 28 November 2016 12:00 | 14 | 2
16 | Yes | Auto Scheduled | Design complete | 0 days | 28 November 2016 12:00 | 28 November 2016 12:00 | 15 | 2
17 | Yes | Auto Scheduled | Mobile Computing DeadLine (Off Work) | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 1
18 | Yes | Auto Scheduled | System Design | 4 days? | 28 November 2016 13:00 | 02 December 2016 12:00 |  | 1
19 | Yes | Auto Scheduled | Review The Two Scenario Specifications | 1 day | 28 November 2016 13:00 | 29 November 2016 12:00 | 16 | 2
20 | Yes | Auto Scheduled | Outline Functional Requirements for both VR Systems | 1 day | 29 November 2016 13:00 | 30 November 2016 12:00 | 19 | 2
21 | Yes | Auto Scheduled | Develop a high level component design for each program | 1 day | 30 November 2016 13:00 | 01 December 2016 12:00 | 20 | 2
22 | Yes | Auto Scheduled | Evalute designs against scenario/functional specifications | 1 day? | 01 December 2016 13:00 | 02 December 2016 12:00 | 21 | 2
23 | Yes | Auto Scheduled | System Design Complete | 0 days | 02 December 2016 12:00 | 02 December 2016 12:00 | 22 | 2
24 | Yes | Auto Scheduled | Christmas Day (Off Work) | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 1
25 | Yes | Auto Scheduled | System Development | 7 days? | 26 October 2016 08:00 | 03 November 2016 17:00 |  | 1
26 | Yes | Auto Scheduled | Sysetm Setup | 7 days | 26 October 2016 08:00 | 03 November 2016 17:00 |  | 2
27 | Yes | Auto Scheduled | Successfully Implement HTC Camera Rig into Unity | 5 days | 26 October 2016 08:00 | 01 November 2016 17:00 |  | 3
28 | Yes | Auto Scheduled | Successfully Implement Leap Motion into Unity | 2 days | 02 November 2016 08:00 | 03 November 2016 17:00 | 27 | 3
29 | Yes | Auto Scheduled | System Development 1 | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
30 | Yes | Auto Scheduled | Load Pre-Made sysetm set-up | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 3
31 | Yes | Auto Scheduled | Create and fill scene accoring to scenario design | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 3
32 | Yes | Auto Scheduled | Implement system design (Evironmental Alteration) | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 3
33 | Yes | Auto Scheduled | System Development 2 | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
34 | Yes | Auto Scheduled | Load Pre-Made sysetm set-up | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 3
35 | Yes | Auto Scheduled | Create and fill scene accoring to scenario design | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 3
36 | Yes | Auto Scheduled | Implement system design (Evironmental Alteration) | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 3
37 | Yes | Auto Scheduled | Start Dissertation Introduction | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 1
38 | Yes | Auto Scheduled | Testing | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 1
39 | Yes | Auto Scheduled | Provide functional testing on system 1 | 0 days | 26 October 2016 08:00 | 26 October 2016 08:00 |  | 2
40 | Yes | Auto Scheduled | Note details of requird revisions | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
41 | Yes | Auto Scheduled | Provide functional testing on system 2 | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
42 | Yes | Auto Scheduled | Note details of requird revisions | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
43 | Yes | Auto Scheduled | System Revisions | 2 days? | 26 October 2016 08:00 | 27 October 2016 17:00 |  | 1
44 | Yes | Auto Scheduled | Implent required revisions on system 1 | 1 day | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
45 | Yes | Auto Scheduled | Go back to testing phase for system 1 | 1 day | 27 October 2016 08:00 | 27 October 2016 17:00 | 44 | 2
46 | Yes | Auto Scheduled | Implent required revisions on system 2 | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
47 | Yes | Auto Scheduled | Go back to testing phase for system 2 | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
48 | Yes | Auto Scheduled | Experiment | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 1
49 | Yes | Auto Scheduled | Gather participants for the experiment | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
50 | Yes | Auto Scheduled | Conduct experiment for system 1 | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
51 | Yes | Auto Scheduled | Conduct experiment for system 2 | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
52 | Yes | Auto Scheduled | Data Analysis | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 1
53 | Yes | Auto Scheduled | Evalute Results | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
54 | Yes | Auto Scheduled | Conduct Results Dissertaion Chapter | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
55 | Yes | Manually Scheduled | Conduct Disseration Conclusions | 103 days | 26 October 2016 08:00 | 17 March 2017 17:00 |  | 1
56 | Yes | Auto Scheduled | Conduct Analysis Chapter | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
57 | Yes | Auto Scheduled | Conduct Discussion Chapter | 1 day? | 26 October 2016 08:00 | 26 October 2016 17:00 |  | 2
58 | Yes | Auto Scheduled | Conduct Conclusions Chapter | 4 days | 09 March 2017 08:00 | 14 March 2017 17:00 |  | 2
59 | Yes | Auto Scheduled | Conduct Future Work Chapter | 3 days | 16 March 2017 08:00 | 20 March 2017 17:00 |  | 2
60 | Yes | Manually Scheduled | Evaluate Dissetation Draft | 12 days | 27 March 2017 08:00 | 09 April 2017 17:00 |  | 1
61 | Yes | Auto Scheduled | Format Dissertation Chapters Into LATEx | 1 day | 29 March 2017 08:00 | 29 March 2017 17:00 |  | 2
62 | Yes | Auto Scheduled | Review Disseration Draft | 3 days | 31 March 2017 08:00 | 03 April 2017 17:00 |  | 2
63 | Yes | Auto Scheduled | Amend Draft Corrections | 6 days | 03 April 2017 08:00 | 09 April 2017 17:00 |  | 2
64 | Yes | Auto Scheduled | Output Final Disseration Piece | 1 day | 10 April 2017 08:00 | 10 April 2017 17:00 |  | 1
65 | Yes | Auto Scheduled | Cross Platorm Module Assesment Focus | 6 days | 24 April 2017 08:00 | 30 April 2017 17:00 |  | 1
66 | Yes | Auto Scheduled | Project Deadline | 1 day | 27 April 2017 08:00 | 27 April 2017 17:00 |  | 1

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Management | M | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Project Manager | P | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Analyst | A | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Developer | D | Work |  |  |  |  | 100% | $0.00/h | 0
5 | Testers | T | Work |  |  |  |  | 100% | $0.00/h | 0
6 | Trainers | T | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Technical Communicators | T | Work |  |  |  |  | 100% | $0.00/h | 0
8 | Deployment Team | D | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Find Appropirate Literature Relating To Human Perception | Management | 0 | 4h | 100%
Identify and Note Sections Which Aid the Project Aim | Management | 0 | 8h | 100%
Analyse Research to Determine Viable Scenarios For Experiment | Analyst | 0 | 40h | 100%
Determine 2 Scenarios To present for the Experiment | Analyst | 0 | 24h | 100%
Gather Resources/Appertus Required To Implement Scenarios. | Project Manager | 0 | 16h | 100%
Develop Storyboard For Data Collection For Scenario 1 | Analyst | 0 | 16h | 100%
Develop Storyboard For Data Collection For Scenario 2 | Analyst | 0 | 40h | 100%
From Both Storyboards Define Experiment Instructions (In Detal) | Analyst | 0 | 32h | 100%
Review The Two Scenario Specifications | Developer | 0 | 8h | 100%
Outline Functional Requirements for both VR Systems | Developer | 0 | 8h | 100%
Develop a high level component design for each program | Developer | 0 | 8h | 100%
Successfully Implement HTC Camera Rig into Unity | Testers | 0 | 40h | 100%
Successfully Implement Leap Motion into Unity | Testers | 0 | 16h | 100%
Implent required revisions on system 1 | Project Manager | 0 | 8h | 100%
Go back to testing phase for system 1 | Project Manager | 0 | 8h | 100%